## ProjectTimeline
PROJECT TIMELINE
| Project Start | 2020-01-01
CATEGORY | TASK | START | END | COLOR | Start | Blue | Red | Green | Brown | Orange | Purple
Concept Dev. | Market Analysis | 2020-01-01 | 2020-01-15 | Blue | 2020-01-01 | 15 | 0 | 0 | 0 | 0 | 0
| Feasibility | 2020-01-15 | 2020-02-05 | Blue | 2020-01-15 | 22 | 0 | 0 | 0 | 0 | 0 | Note:Colors defined Tak of each category
| Rough Prototypes | 2020-02-06 | 2020-02-26 | Blue | 2020-02-06 | 21 | 0 | 0 | 0 | 0 | 0 | Example:
| Cost Estimates | 2020-01-20 | 2020-03-01 | Blue | 2020-01-20 | 42 | 0 | 0 | 0 | 0 | 0 | 1)Blue is a task from concept Dev.
System Design | Architectures | 2020-02-01 | 2020-02-15 | Red | 2020-02-01 | 0 | 15 | 0 | 0 | 0 | 0 | 2)Red is a task from System Design
| Sub-systems | 2020-02-05 | 2020-02-22 | Red | 2020-02-05 | 0 | 18 | 0 | 0 | 0 | 0
| Refine Design | 2020-02-23 | 2020-03-05 | Red | 2020-02-23 | 0 | 12 | 0 | 0 | 0 | 0
| Make-buy analysis | 2020-03-06 | 2020-03-09 | Red | 2020-03-06 | 0 | 4 | 0 | 0 | 0 | 0
Detail Design | Complete Definition | 2020-03-10 | 2020-04-09 | Green | 2020-03-10 | 0 | 0 | 31 | 0 | 0 | 0
| Materials | 2020-03-10 | 2020-03-20 | Green | 2020-03-10 | 0 | 0 | 11 | 0 | 0 | 0
| Tooling | 2020-03-20 | 2020-04-09 | Green | 2020-03-20 | 0 | 0 | 21 | 0 | 0 | 0
| Quality Control Def. | 2020-04-10 | 2020-04-15 | Green | 2020-04-10 | 0 | 0 | 6 | 0 | 0 | 0
Test & Refine | Field Testing | 2020-03-20 | 2020-04-04 | Brown | 2020-03-20 | 0 | 0 | 0 | 16 | 0 | 0
| Regulations | 2020-03-20 | 2020-04-19 | Brown | 2020-03-20 | 0 | 0 | 0 | 31 | 0 | 0
| Refine Processes | 2020-04-05 | 2020-04-20 | Brown | 2020-04-05 | 0 | 0 | 0 | 16 | 0 | 0
Produce | Key Customers | 2020-04-21 | 2020-04-26 | Orange | 2020-04-21 | 0 | 0 | 0 | 0 | 6 | 0
| Evaluate | 2020-04-21 | 2020-05-02 | Orange | 2020-04-21 | 0 | 0 | 0 | 0 | 12 | 0
| Begin Full Production | 2020-05-03 | 2020-05-03 | Orange | 2020-05-03 | 0 | 0 | 0 | 0 | 1 | 0
Other | Economic Analysis | 2020-01-01 | 2020-02-28 | Purple | 2020-01-01 | 0 | 0 | 0 | 0 | 0 | 59
| Legal / Regulatory | 2020-01-01 | 2020-04-19 | Purple | 2020-01-01 | 0 | 0 | 0 | 0 | 0 | 110
| Sales Plan / Train | 2020-03-01 | 2020-04-29 | Purple | 2020-03-01 | 0 | 0 | 0 | 0 | 0 | 60
Insert new rows above this one
| MILESTONE LABEL | DATE | Margin Bottom | Margin Top
| Milestone 1 | 2020-03-02 | 50% | 95%
| Milestone 2 | 2020-04-01 | 25% | 95%
| Milestone 3 | 2020-05-04 | 10% | 95%
| Milestone 4 |  | 30% | 95%
Formulas:
Start = IF(ISBLANK([START]),0,[START])